## Project Charter
Project Charter: ManCave Creation
Project Manager: Porky Pig
For Bugs Bunny’s Entertainment Room
DATE: 03/28/2025
Project Summary
The Man Cave Creation project aims to design and build a personalized and comfortable space within a budget of $50,000.00. The project will include memorabilia, a saltwater fish tank, a 77+ inch screen TV with additional TVs for viewing multiple games, a high-quality sound system, a carrot juice bar with refrigerator, and a state-of-the-art security system. The goal is to create a fully furnished and decorated man cave that provides a relaxing and enjoyable environment.
Project Goals
To create a personalized and comfortable man cave.
To include memorabilia, a saltwater fish tank, a 77+ inch screen TV, Additional TVs around the room, bar, and a sound system within the budget.
Deliverables
· A fully furnished and decorated man cave.
· A functioning saltwater fish tank.
· A high-definition 77+ inch OLED screen TV.
· Four High-definition TVs around the room.
· A high-quality sound system.
· A high-quality Security System.
· A Bar for Carrot Juice and Carrots
Scope and Exclusion
In-Scope:
Design and layout of the man cave.
Detail cleaning and painting of Man Cave
Selection and purchase of memorabilia.
Installation of a saltwater fish tank.
Purchase and installation of a 77+ inch screen TV.
Additional TVs around the room.
Purchase and installation of Stadium/Theater seating for Eight.
Purchase and installation of a sound system.
Purchase and instllation of Carrot Juice Bar
Out-of-Scope:
● Major structural changes to the room.
● Extensive electrical rewiring
● Purchase of additional furniture beyond the specified items.
● Landscaping or exterior modifications.
● Any items or features not explicitly mentioned in the project scope.
Benefits & Costs
Benefits:
Creation of a personalized and comfortable space for relaxation and entertainment.
Increased property value due to the addition of a high-quality man cave.
Enhanced enjoyment and satisfaction from having a dedicated space for hobbies and leisure activities.
Potential for hosting gatherings and social events in a well-equipped environment.
Costs:
Initial investment of $75,000.00 for the design, purchase, and installation of all items.
Complete cleaning and repainting of room
Ongoing maintenance costs for the saltwater fish tank.
Potential additional costs if any unforeseen issues arise during the project, such as structural modifications or delays in delivery.
Total Estimated Budget: $75,000.00
Timeline:
Project initiation: May 1, 2025
Design and planning: May 1, 2025 – June 1, 2025
Procurement of items: June 1, 2025 – July 1, 2025
Installation and setup: July 1, 2025 – August 25, 2025
Project completion: September 1, 2025
Risk and Assumptions:
Risk of exceeding the budget.
Assumption that all items will be available for purchase within the budget.
Risk of delays in delivery and installation.
Stakeholders:
Project Owner: Bugs Bunny, Lola Bunny,
Project Sponsor: Tom and Jerry
Date: March 31, 2025
Appendix:
Porky Pig 5/1
Bugs Bunny 5/1
Lola Bunny 5/1
Porky Pigs ManCave Productions
Porky Pigs ManCave Productions

## Tasks and Timeline
Bugs Man Cave
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [19 empty] | PHASE TWO | [19 empty] | PHASE THREE | [19 empty] | PHASE FOUR | [19 empty] | PHASE FIVE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 | WEEK 16
[7 empty] | M | T | W | 2025-05-01 | 2025-05-02 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-09-01 |  | F
Phase 1: Project Initiation & Initial Planning (Before/Around May 1, 2025) |  | 2025-05-01 | 2025-06-01
Project Kick off Meeting |  | 2025-05-01 | 2025-05-01 | 1
Detailed Requirements Gathering |  | 2025-05-02 | 2025-05-06 | 4
Room Assessment |  | 2025-05-02 | 2025-05-06 | 4
Budget Allocation |  | 2025-05-07 | 2025-05-13 | 6
Develop Detailed Project Schedule: |  | 2025-05-14 | 2025-05-20 | 6
Phase 2: Design and Planning (May 1, 2025 – June 1, 2025) |  | 2025-05-14 | 2025-06-01
Develop Man Cave Layout Options |  | 2025-05-14 | 2025-05-20 | 6
Finalize Layout Design |  | 2025-05-21 | 2025-05-23 | 2
Select Finishes: |  | 2025-05-21 | 2025-05-23 | 2
Design Bar: |  | 2025-05-22 | 2025-05-28 | 6
Plan AV & Security Wiring |  | 2025-05-27 | 2025-05-30 | 3
Phase 3: Procurement of Items (June 1, 2025 – July 1, 2025) |  | 2025-06-02 | 2025-07-01
Vendor Research & Selection |  | 2025-06-02 | 2025-06-09 | 7
Purchase Audio-Visual Equipment |  | 2025-06-10 | 2025-06-16 | 6
Purchase Furniture |  | 2025-06-10 | 2025-06-16 | 6
Purchase Fish Tank & Equipment |  | 2025-06-11 | 2025-06-17 | 6
Purchase Bar Components: |  | 2025-06-12 | 2025-06-18 | 6
Purchase Security System |  | 2025-06-12 | 2025-06-18 | 6
Select & Purchase Memorabilia |  | 2025-06-16 | 2025-06-27 | 11
Schedule Deliveries & Installations |  | 2025-06-17 | 2025-06-30 | 13
Purchase Supplies |  | 2025-06-23 | 2025-06-27 | 4
Phase 4: Installation and Setup (July 1, 2025 – August 25, 2025) |  | 2025-07-01 | 2025-08-25
Room Preparation |  | 2025-07-01 | 2025-07-02 | 2
Install Flooring (If Applicable/Included)/Paint |  | 2025-07-03 | 2025-07-10 | 7
Install & Set Up Fish Tank: |  | 2025-07-11 | 2025-07-16 | 5
Install Security System |  | 2025-07-17 | 2025-07-23 | 6
Install Audio-Visual Systems: |  | 2025-07-24 | 2025-08-04 | 7
Install Furniture: |  | 2025-08-05 | 2025-08-08 | 3
Install Bar |  | 2025-08-11 | 2025-08-14 | 3
Decorate & Furnish: |  | 2025-08-15 | 2025-08-21 | 6
Introduce Fish (Post-Cycling) |  | 2025-08-21 | 2025-08-22 | 2
Phase 5: Project Completion & Handover (August 26, 2025 – September 1, 2025) |  | 2025-08-25 | 2025-08-27
System Testing & Quality Check |  | 2025-08-25 | 2025-09-01 | 7
Final Cleaning |  | 2025-08-28 | 2025-08-27 | 1
Documentation & Training |  | 2025-08-28 | 2025-08-29 | 2
Final Walkthrough & Acceptance: |  | 2025-08-29 | 2025-08-29 | 1
Budget Reconciliation |  | 2025-08-26 | 2025-08-29 | 3
Project Closure: |  | 2025-09-01 | 2025-09-01 | 1
1903-05-09

## Kanban Board
Task | To Do | In Progress | Done
Project Kick off Meeting |  |  | X
Detailed Requirements Gathering |  |  | X
Room Assessment |  |  | X
Budget Allocation |  |  | X
Develop Detailed Project Schedule: |  |  | X
Develop Man Cave Layout Options |  |  | X
Finalize Layout Design |  |  | X | Porky Pig
Select Finishes: |  |  | X
Design Bar: |  |  | X
Plan AV & Security Wiring |  |  | X
Vendor Research & Selection |  |  | X
Purchase Audio-Visual Equipment |  |  | X
Purchase Furniture |  |  | X
Purchase Fish Tank & Equipment |  |  | X
Purchase Bar Components: |  |  | X
Purchase Security System |  |  | X
Select & Purchase Memorabilia |  |  | X
Schedule Deliveries & Installations |  |  | X
Purchase Supplies |  |  | X
Room Preparation |  | X
Install Flooring (If Applicable/Included)/Paint |  | X
Install & Set Up Fish Tank: |  | X
Install Security System |  | X
Install Audio-Visual Systems: |  | X
Install Furniture: |  | X
Install Bar |  | X
Decorate & Furnish: |  | X
Introduce Fish (Post-Cycling) |  | X
System Testing & Quality Check | X
Final Cleaning | X
Documentation & Training | X
Final Walkthrough & Acceptance: | X
Budget Reconciliation | X
Project Closure: | X
KANBAN BOARD
For Bugs Bunny Man Cave

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates

## Milestones
Milestones
No. | Position | Date | Milestone
1 |  |  | Phase 1: Project Initiation & Initial Planning (Before/Around May 1, 2025)
2 |  |  | Phase 2: Design and Planning (May 1, 2025 – June 1, 2025)
3 |  |  | Phase 3: Procurement of Items (June 1, 2025 – July 1, 2025)
4 |  |  | Phase 4: Installation and Setup (July 1, 2025 – August 25, 2025)
5 |  |  | Phase 5: Project Completion & Handover (August 26, 2025 – September 1, 2025)
6
7

## Stakeholder Grid
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Porky Pig
Bug Bunny
Lola Bunny
Interest
med
Tom and Jerry
All Vendors

## Risk Register
Risk ID | Risk Description | What is the risk/opportunity that... | How the risk/opportunity will affect the project... | Category | Priority | Impact | PI Score | Response Strategy | What action will mitigate the risk? | Risk Owner | Date Logged | Status | Last Review Date | Date Closed
R01 | Budget Overrun | What if project costs exceed the approved $75,000 budget? | Project may halt, require scope reduction, or cause stakeholder dissatisfaction. | Budget | H | H | Critical | Mitigate / Avoid | 1. Review scope/budget immediately (seating, designer fee). 2. Identify cost savings. 3. Track budget strictly. 4. Prepare variance report/funding request if needed. | Porky Pig | 2025-03-29 | Open
R02 | Vendor Delivery Delays | What if key components (TVs, seating, aquarium, bar) are delivered late? | Installation schedule will be disrupted, potentially delaying project completion. | Schedule | M | H | High | Mitigate | 1. Confirm lead times early. 2. Build schedule buffer. 3. Communicate regularly with vendors. 4. Identify backup vendors if possible. | Porky Pig | 2025-03-29 | Open
R03 | Scope Creep | What if Owners request new features/changes after planning is complete? | Budget and schedule may increase, potentially exceeding limits. | Scope | M | H | High | Avoid / Mitigate | 1. Get clear sign-off on scope baseline. 2. Implement formal change request process. 3. Communicate scope boundaries clearly. | Porky Pig | 2025-03-29 | Open
R04 | Extended Aquarium Cycle Time | What if the saltwater tank nitrogen cycle takes longer than 4-6 weeks? | Fish introduction delayed, potentially impacting final acceptance/completion date. | Schedule | M | M | Medium | Mitigate / Accept | 1. Start cycling process early. 2. Use established methods (live rock). 3. Monitor parameters closely. 4. Inform Owners of potential variability. | Porky Pig | 2025-03-29 | Open
R05 | AV Integration Issues | What if AV components (TVs, sound system, sources) don't work together well? | System functionality impaired, rework needed, user dissatisfaction. | Technical | M | M | Medium | Mitigate | 1. Select compatible equipment. 2. Use experienced AV installer. 3. Allocate sufficient testing time. 4. Verify specific multi-game viewing requirements are met. | Porky Pig | 2025-03-29 | Open
R06 | Specific Item Unavailability | What if specific high-end items (83" TV, seating) are unavailable? | Procurement delayed, requires finding/approving alternatives, potential cost impact. | Resource | L | H | Medium | Mitigate / Accept | 1. Confirm availability/lead times early. 2. Identify acceptable alternatives during procurement. 3. Get Owner approval for substitutions. | Porky Pig | 2025-03-29 | Open
R07 | Aquarium Leak / Malfunction | What if the aquarium leaks or equipment fails after setup? | Water damage, loss of livestock, costly repairs/replacement, schedule delays. | Technical | L | H | Medium | Mitigate / Transfer | 1. Use reputable vendor/installer. 2. Ensure proper testing. 3. Verify warranties. 4. Consider leak detection integration. | Porky Pig | 2025-03-29 | Open
R08 | Installation Service Delays | What if installers (AV, paint, plumbing) take longer than scheduled? | Delays subsequent tasks, pushes out overall schedule, potential cost increases. | Schedule | M | M | Medium | Mitigate | 1. Get detailed time estimates. 2. Ensure site readiness. 3. Coordinate installers effectively. 4. Build schedule buffer. | Porky Pig | 2025-03-29 | Open
R09 | Owner Disagreement | What if Bugs and Lola disagree on design choices or features? | Decision-making delayed, potential for rework or scope changes. | Stakeholder | L | M | Low | Mitigate | 1. Involve both Owners in key reviews/decisions. 2. Document approvals. 3. Facilitate consensus-building. | Porky Pig | 2025-03-29 | Open
R10 | Delivery Damage | What if equipment or materials are damaged during transport? | Replacement needed, causing schedule delays and potential cost increases (if not insured). | External | L | M | Low | Mitigate / Transfer | 1. Inspect deliveries immediately. 2. Ensure vendor shipping insurance. 3. Document damage thoroughly for claims. | Porky Pig | 2025-03-29 | Open
R11 | Unexpected Minor Site Issues | What if minor site issues arise needing work outside exclusions? | Minor delays, requires use of contingency funds. | Budget/Scope | L | M | Low | Mitigate / Accept | 1. Perform thorough room assessment. 2. Utilize contingency budget ($10,000). 3. Assess if change request needed vs. using buffer. | Porky Pig | 2025-03-29 | Open

## Stakeholder Register
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes
Bugs Bunny | Product Owner | H | H | Role: Primary recipient and user of the Man Cave. Co-owner.
Interest: Very High. The project is for his direct benefit, enjoyment, and relaxation. Deeply invested in the features, design, and final outcome meeting his personal vision.
Influence: Very High. As the primary owner and end-user, his decisions on design, features, and final acceptance are critical. Can directly impact scope and direction.
Key Needs/Expectations: A personalized, comfortable space meeting all specified deliverables (large TV, additional TVs, sound system, fish tank, bar, security, memorabilia display), functionality for entertainment, timely completion, adherence to his vision.
Management Strategy: Manage Closely. Requires frequent communication, active involvement in key design and feature decisions, regular updates, and formal sign-off at key milestones.
Lola Bunny | Product Owner | H | H | Role: Co-owner of the property.
Interest: High. While primarily for Bugs, she likely has a strong interest in the project's impact on the home's overall aesthetics, value, budget adherence.
Influence: High. As a co-owner, she likely shares decision-making power, especially regarding budget, major aesthetic choices, and final approval.
Key Needs/Expectations: An outcome that is aesthetically pleasing, fits within the home's context, stays within budget
Management Strategy: Manage Closely. Similar to Bugs, requires regular communication and involvement in key decisions.
Tom and Jerry | Project Sponsor | H | M/H | Role: Providing sponsorship
Interest: Medium to High. Invested in the project's successful completion within the agreed parameters (scope, budget, timeline)..
Influence: High. As sponsors, they likely hold significant authority, potentially controlling the budget, approving major scope changes, and providing final go-ahead or resources.
Key Needs/Expectations: Project success, adherence to budget ($75,000) and timeline (completion by Sept 1, 2025), clear communication on progress and issues (especially financial), responsible management of resources.
Management Strategy: Keep Satisfied/Informed. Provide regular, concise status reports focusing on budget, schedule, and major milestones/risks. Escalate critical issues or decisions requiring their input promptly. Demonstrate fiscal responsibility.
Porky Pig | Project Manager | H | H | Role: Responsible for planning, executing, monitoring, and closing the project.
Interest: Very High. Directly responsible for delivering the project successfully according to the charter.
Influence: Medium to High. Manages daily operations, directs resources (implicitly), manages risks, and controls project communication flow.
Key Needs/Expectations: Clear scope and requirements, timely decisions from owners/sponsors, cooperation from any potential vendors/installers, ability to manage risks and resources effectively, achieving the project goals within constraints.
Management Strategy: (Self-Management) Maintain clear communication channels, proactively manage risks, track progress diligently, facilitate decision-making,
Foghorn Leghorm | Vendor | L | M | Role:
Interest: Fulfilling their contractual obligations, getting paid on time, maintaining a good business reputation, and potentially securing future business
Influence: Low. Their influence is concentrated on their specific area of contribution.
Key Needs/Expectations: Clear scope and requirements.A clear agreement outlining the scope, deliverables, timelines, price, and terms.To be compensated for their goods and services as agreed.Predictability to manage their own resources, inventory, and staff allocation.bility to perform their work efficiently and safel
Management Strategy: Keep Satisfied/Informed. Provide regular, concise status reports focusing on schedule.
Wyle E Coyote | Vendor | L | M
Interest: Fulfilling their contractual obligations, getting paid on time, maintaining a good business reputation, and potentially securing future business
Influence: Low. Their influence is concentrated on their specific area of contribution.
Key Needs/Expectations: Clear scope and requirements.A clear agreement outlining the scope, deliverables, timelines, price, and terms.To be compensated for their goods and services as agreed.Predictability to manage their own resources, inventory, and staff allocation.bility to perform their work efficiently and safel
Management Strategy: Keep Satisfied/Informed. Provide regular, concise status reports focusing on schedule.
Roadrunner | Vendor | L | M
Interest: Fulfilling their contractual obligations, getting paid on time, maintaining a good business reputation, and potentially securing future business
Influence: Low. Their influence is concentrated on their specific area of contribution.
Key Needs/Expectations: Clear scope and requirements.A clear agreement outlining the scope, deliverables, timelines, price, and terms.To be compensated for their goods and services as agreed.Predictability to manage their own resources, inventory, and staff allocation.bility to perform their work efficiently and safel
Management Strategy: Keep Satisfied/Informed. Provide regular, concise status reports focusing on schedule.
Beaker | Vendor | L | M
Interest: Fulfilling their contractual obligations, getting paid on time, maintaining a good business reputation, and potentially securing future business
Influence: Low. Their influence is concentrated on their specific area of contribution.
Key Needs/Expectations: Clear scope and requirements.A clear agreement outlining the scope, deliverables, timelines, price, and terms.To be compensated for their goods and services as agreed.Predictability to manage their own resources, inventory, and staff allocation.bility to perform their work efficiently and safel
Management Strategy: Keep Satisfied/Informed. Provide regular, concise status reports focusing on schedule.
Kermit the Frog | Vendor | L | M
Interest: Fulfilling their contractual obligations, getting paid on time, maintaining a good business reputation, and potentially securing future business
Influence: Low. Their influence is concentrated on their specific area of contribution.
Key Needs/Expectations: Clear scope and requirements.A clear agreement outlining the scope, deliverables, timelines, price, and terms.To be compensated for their goods and services as agreed.Predictability to manage their own resources, inventory, and staff allocation.bility to perform their work efficiently and safel
Management Strategy: Keep Satisfied/Informed. Provide regular, concise status reports focusing on schedule.
Gonzo | Vendor | L | M
Interest: Fulfilling their contractual obligations, getting paid on time, maintaining a good business reputation, and potentially securing future business
Influence: Low. Their influence is concentrated on their specific area of contribution.
Key Needs/Expectations: Clear scope and requirements.A clear agreement outlining the scope, deliverables, timelines, price, and terms.To be compensated for their goods and services as agreed.Predictability to manage their own resources, inventory, and staff allocation.bility to perform their work efficiently and safel
Management Strategy: Keep Satisfied/Informed. Provide regular, concise status reports focusing on schedule.
Pepe LePew | Vendor | L | M
Interest: Fulfilling their contractual obligations, getting paid on time, maintaining a good business reputation, and potentially securing future business
Influence: Low. Their influence is concentrated on their specific area of contribution.
Key Needs/Expectations: Clear scope and requirements.A clear agreement outlining the scope, deliverables, timelines, price, and terms.To be compensated for their goods and services as agreed.Predictability to manage their own resources, inventory, and staff allocation.bility to perform their work efficiently and safel
Management Strategy: Keep Satisfied/Informed. Provide regular, concise status reports focusing on schedule.
Tazmaina Devil | Vendor | L | M
Interest: Fulfilling their contractual obligations, getting paid on time, maintaining a good business reputation, and potentially securing future business
Influence: Low. Their influence is concentrated on their specific area of contribution.
Key Needs/Expectations: Clear scope and requirements.A clear agreement outlining the scope, deliverables, timelines, price, and terms.To be compensated for their goods and services as agreed.Predictability to manage their own resources, inventory, and staff allocation.bility to perform their work efficiently and safel
Management Strategy: Keep Satisfied/Informed. Provide regular, concise status reports focusing on schedule.
Fozzie Bear | Vendor | L | M
Interest: Fulfilling their contractual obligations, getting paid on time, maintaining a good business reputation, and potentially securing future business
Influence: Low. Their influence is concentrated on their specific area of contribution.
Key Needs/Expectations: Clear scope and requirements.A clear agreement outlining the scope, deliverables, timelines, price, and terms.To be compensated for their goods and services as agreed.Predictability to manage their own resources, inventory, and staff allocation.bility to perform their work efficiently and safel
Management Strategy: Keep Satisfied/Informed. Provide regular, concise status reports focusing on schedule.
Daffy Duck | Vendor | L | M
Interest: Fulfilling their contractual obligations, getting paid on time, maintaining a good business reputation, and potentially securing future business
Influence: Low. Their influence is concentrated on their specific area of contribution.
Key Needs/Expectations: Clear scope and requirements.A clear agreement outlining the scope, deliverables, timelines, price, and terms.To be compensated for their goods and services as agreed.Predictability to manage their own resources, inventory, and staff allocation.bility to perform their work efficiently and safel
Management Strategy: Keep Satisfied/Informed. Provide regular, concise status reports focusing on schedule.

## Resource Page
RESOURCE REQUIREMENTS
PROJECT DETAILS
PROJECT No: | BD1
DATE: | 2025-03-29
FULL PROJECT NAME: | Bugs Bunny Man Cave
PROJECT MANAGER: | Porky Pig
PROJECT SPONSOR: | Bugs Bunny
1. Introduction | This Resource Plan identifies and outlines the necessary resources required for the successful execution of the ManCave Creation project for Bugs Bunny. Resources include human personnel, equipment, materials, facilities, and financial budget. The plan aims to ensure resources are available when needed and are utilized effectively throughout the project lifecycle (May 1, 2025 – September 1, 2025).
2. Financial Resources | Total Estimated Budget: $75,000.00
Source: Project Sponsors (Tom and Jerry)
Management: Porky Pig is responsible for tracking expenditures against the budget. A detailed budget breakdown allocating funds to specific categories (AV equipment, furniture, fish tank, bar, security, labor, materials, contingency) should be maintained separately.

## Resource Page 2
3. Human Resources |  |  |  |  | 4. Equipment Resources
Role | Specific Resource | Source/Acquisition | Timing / Key Phase(s) | Key Responsibilities | Equipment Type | Specific Item(s) | Source/Acquisition | Timing / Key Phase(s) | Notes
Project Manager | Porky Pig | Assigned | Full Project Duration | Planning, coordination, budget, schedule, risk mgmt, vendor mgmt, communication | Project Management Tools | Computer, PM Software, Communication tools | Porky Pig Provided | Full Project Duration | For planning, tracking, communication
Project Owner(s) | Bugs Bunny, Lola Bunny | Stakeholder | Full Project Duration | Provide input, requirements, approvals (design, purchases, final acceptance) | Cleaning Equipment | Vacuum, Mop, Buckets, Cleaning cloths | Marvin the Martain | Installation Phase | Required for cleaning tasks
Project Sponsor(s) | Tom and Jerry | Stakeholder | Full Project Duration | Provide oversight, funding, major approvals | Painting Equipment | Brushes, Rollers, Trays, Drop cloths, Ladder | Daffy Duck | Installation Phase | Required for painting tasks
Design Support | Tom and Jerry | Stakeholder | Planning & Design Phase | Create room layouts, select finishes (if Porky cannot perform, allocate budget) | Installation Tools (General) | Drills, Level, Screwdrivers, Ladders, etc. | Installer Provided | Installation Phase | Assumption: Most specialized installers will provide their own tools
Cleaning Crew | Marvin the Martian | External Hire | Installation Phase (Start/End) | Detailed cleaning before painting, final cleaning before handover | Installation Tools (Specific) | AV wiring tools, Fish tank plumbing tools, etc. | Installer Provided | Installation Phase | Confirm with vendors if any specific tools need project provision
Painters | Daffy Duck | External Hire | Installation Phase | Prepare surfaces, paint room according to specifications | Deliverable Equipment | TVs, Sound System, Fish Tank System, Security System | Purchase (Budgeted) | Procurement & Installation | These are project deliverables but function as equipment during setup/test
AV Installation | Foghorn Leghorn Tazmain Devil | Vendor / Hire | Installation Phase | Mount TVs, install sound system components, run wiring, configure system
Fish Tank Specialist | Pepe LePew | Vendor / Hire | Installation Phase | Deliver, set up tank/equipment, guide cycling process, potentially stock
Security System Installer | Droopy | Vendor / Hire | Installation Phase | Install cameras, sensors, control panel, configure system
Furniture Assembly | Wyle E Coyote | Vendor / Hire | Installation Phase | Assemble and position stadium seating
Bar Installation | Fozzie Bear | Vendor / Hire | Installation Phase | Assemble/install bar structure, potentially connect refrigerator
General Labor (Optional) | TBD | External Hire | Installation Phase (as needed) | Assist with moving heavy items, site cleanup, support installers

## Resource Page 3
5. Material Resources
Material Type | Specific Item(s) | Source/Acquisition | Timing / Key Phase(s) | Notes | 6. Facilities Resources | Primary Facility: Designated room within Bugs Bunny's residence.
Paint & Sundries | Primer, Paint (colors TBD), Caulk, Tape, Patching compound | Purchase (Budgeted) | Installation Phase | Quantity based on room size and paint selection |  | Requirement: Access must be coordinated with Bugs and Lola Bunny for planning, measurements, and throughout the installation phase.
Cleaning Supplies | Cleaning solutions, sponges, trash bags | Purchase (Budgeted) | Installation Phase | Consumables |  | Assumption: The room is structurally sound and has adequate basic electrical service (no major rewiring needed per exclusions)
Wiring & Connectors | Speaker wire, HDMI cables, Network cables, Connectors, Mounts | Purchase (Budgeted) | Procurement & Installation | For AV and Security systems installation
Fish Tank Consumables | Salt mix, Substrate, Water conditioners, Test kits, Food | Purchase (Budgeted) | Installation Phase | For initial setup and cycling | 7. Assumptions | The $75,000 budget is approved and funds will be available as needed.
Bar Supplies (Initial Stock) | Carrots, Juice ingredients, basic glassware | Purchase (Budgeted) | Finalization Phase | Part of delivering a functional bar |  | Porky Pig has the capacity to manage the project and coordinate vendors/tasks.
Project Deliverables | Memorabilia, Seating, Bar Structure, Refrigerator | Purchase (Budgeted) | Procurement & Installation | Core items forming the Man Cave |  | Bugs and Lola Bunny will be available for timely input and approvals.
Vendors for specialized installation (AV, Security, Fish Tank) will provide necessary expertise and standard tools.
External labor (cleaning, painting, general) can be sourced within budget.
Required materials and equipment deliverables will be available for purchase within the timeline.

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes | Vendor | Total Labor/Installation | Total Cost
LG OLED evo M Series 83-Inch Class 4K Smart TV with Wireless Video & Audio Transfer | https://www.lg.com/us/tvs/lg-oled83m3pua-oled-4k-tv | 2025-03-31 | 5499.99 | Foghorns TV's | 100 | 5599.99
55 inch Class LG OLED AI B4 4K Smart TV 2024 | https://www.lg.com/us/tvs/lg-oled55b4pua-oled-4k-tv | 2025-03-31 | 4 TV's at $999.99 each Total price $3999.96 | Foghorns TV's | 400 | 4399.96
Bose Surround Speakers 700 | https://www.bose.com/p/home-theater/bose-surround-speakers-700/SS700-SPEAKERWIRELESS.html?dwvar_SS700-SPEAKERWIRELESS_color=BOSE+BLACK&quantity=1 | 2025-03-31 | 2 sets at $599.00 each Total price $1198 | Tazs Loud Sound | 100 | 1298
Bose Surround Speakers | https://www.bose.com/p/home-theater/surround-speakers--pair--uscanada/SS-SPEAKERWIRELESS-BBLK-120V-AST.html | 2025-03-31 | 2 sets at $399.00 each Total price $798 | Tazs Loud Sound | 100 | 898
Bliss LHR Massage with Riser | https://www.bose.com/p/home-theater/surround-speakers--pair--uscanada/SS-SPEAKERWIRELESS-BBLK-120V-AST.html | 2025-03-31 | 8216 | ACME Furniture | 0 | 8216
Bliss LHR Massage without Riser | https://www.bose.com/p/home-theater/surround-speakers--pair--uscanada/SS-SPEAKERWIRELESS-BBLK-120V-AST.html | 2025-03-31 | 6996 | ACME Furniture | 0 | 6996
300 Gallon* Glass Saltwater Aquarium Details | https://www.customaquariums.com/product/300-gallon-glass-saltwater-aquarium/ | 2025-03-31 | 6589.11 | Kermits Aquariums | 500 | 7089.11
Detail Cleaning of Room |  | 2025-03-31 | 350 |  | 0 | 350
Security System with 5 year contract |  | 2025-03-31 | Security System $1000 with contract additional $1800 Total $2800 | Droopy Security | 0 | 2800
Designers |  | 2025-03-31 | 5000 | Tom and Jerry Designs | 0 | 5000
Painting of Room |  | 2025-03-31 | 500 | Ducks Painting Service | 0 | 500
Assorted Fish and Coral/Service Contract for 5 years | https://www.saltwaterfish.com/ | 2025-03-31 | Fish cost $500 with contract additional $4000 total of $4500 | Fine Fish Emporium | 0 | 4500
Sports Memorabilia | GSM.com | 2025-03-31 | 7500 | Gonzos Sports Icons | 0 | 7500
Bar with Taps | https://www.bbqguys.com | 2025-03-31 | 5299 | Fozzies Good Times | 0 | 5299
Plumbing of Bar |  | 2025-03-31 | $750.00 after the installation of the bar | Bleakers Plumbing | 0 | 750
Transportation | Beep Beep.com | 2025-03-31 | 250 | Beep Beep Transportation | 250 | 500
[5 empty] | Total Cost | 61696.06
[5 empty] | Buffer | 10000
71696.06

## Budget
Porky Pig
Category | Item / Description | Vendor | Item Cost | Labor/Install Cost | Total Cost | Notes
Audio/Visual Equipment
| LG OLED 83" M Series TV | Foghorns TVs | 5499.99 | 100 | 5599.99
| 55" LG OLED TV (4 units @ $999.99) | Foghorns TVs | 3999.96 | 400 | 4399.96
| Bose Surround Speakers 700 (2 sets) | Tazs Loud Sound | 1198 | 100 | 1298
| Bose Surround Speakers (Other Model) (2 sets @ $399) | Tazs Loud Sound | 798 | 100 | 898
Furniture
| Bliss LHR Massage Seating with Riser 4 Seats | ACME Furniture | 8216 | 0 | 8216
| Bliss LHR Massage Seating without Riser 4 Seats | ACME Furniture | 6996 | 0 | 6996
Aquarium & Livestock
| 300 Gallon Glass Saltwater Aquarium | Kermits Aquariums | 6589.11 | 500 | 7089.11
| Assorted Fish/Coral + 5yr Service Contract | Fine Fish Emporium | 4500 | 0 | 4500 | Includes $500 fish, $4000 contract
Bar Setup
| Bar with Taps | Fazzies Good Times | 5299 | 0 | 5299
| Plumbing for Bar | Bleakers Plumbing | 0 | 750 | 750 | Service after bar installation
Room Preparation
| Detail Cleaning of Room | Distruction Cleaners |  | 350 | 350
| Painting of Room | Ducks Painting Service |  | 500 | 500
Security System
| Security System Hardware + 5yr Contract | Droopy Security | 2800 | 0 | 2800 | Includes $1000 system, $1800 contract
Memorabilia
| Sports Memorabilia | Gonzos Sports icons | 7500 | 0 | 7500
Services & Other
| Designers Fee | Tom and Jerry Designs | 5000 | 0 | 5000
| Transportation/Unloading | Beep Beep Transportation | 250 | 250 | 500
SUBTOTAL (Based on Lines) |  |  |  |  | 61696.06
Contingency / Buffer |  |  |  |  | 10000
GRAND TOTAL (Estimated) |  |  |  |  | 71696.06
Bugs Man Cave

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5

## Artifacts
Stakeholders | Role
Bugs Bunny | Owner
Lola Bunny | Co-owner
Tom and Jerry | Designers
Porky Pig | Project Manager
Team Members | Vendor | Bids | Notes
Foghorn Leghorn | Foghorns TVs
Wyle E Coyote | ACME Furniture
Road Runner | Beep Beep Transportation
Beaker | Beakers Plumbing
Kermit the Frog | Kermits Aquariums
Gonzo | Gonzos Sports Icons
Pepe LePew | Fine Fish Emporium
Tazmainia Devil | Tazs Loud Sound
Fozzie Bear | Fozzies Good Times
Droopy Dog | Droopy's Security
Daffy Duck | Ducks Painting Service
Marvin the Martian | Destruction Cleaners

## Knowledge Management Summary
Knowledge Management Summary: ManCave Creation
| Bugs ManCave by Porky Pig | Porky Pig
1. Purpose | To capture key documents, insights, and lessons learned from the ManCave Creation project for future reference, improving planning and execution of similar projects undertaken by Porky Pig or sponsored by Tom and Jerry.
2. Key Documents Created & Archived | The following project documents should be archived in a central location (e.g., "Completed Projects\ManCave Creation" on a shared drive or project management tool):
Project Charter
Detailed Task List / Work Breakdown Structure (WBS)
Resource Plan
Project Schedule (Planned vs. Actual)
Budget Documents (Initial estimates [incl. image analysis], Final Actual Costs, Budget Tracking Sheet showing buffer usage)
Risk Register (Initial)
Design & Layout Plans (Final version)
Vendor List (Contact info, items/services provided, contracts/POs, performance notes)
Key Communication Records (e.g., Change Requests if any, key decisions)
System Manuals & Warranties (AV, Aquarium, Security, Appliances)
Training Materials (provided to Bugs Bunny)
Project Post-Mortem Report (This document)
Final Acceptance/Sign-off Form
3. Key Lessons Learned Summary |  | Perform exhaustive initial site assessments, checking floors/walls/utilities.
Contingency buffers (10-15%) are essential for renovation risks.
Diligent vendor coordination is critical for multi-trade projects.
Strong budget management can overcome initial high estimates.
4. Storage Location | [Specify Location – No Documents available]
5. Keywords for Search |  | Man Cave, Bugs Bunny, Renovation, Project Management, AV Install, Home Theater, Saltwater Aquarium, Budget Management, Risk Management, Vendor List 2025, Lessons Learned, Porky Pig, Tom and Jerry

## Post-Mortem
Post-Mortem: Bugs ManCave
Porky Pig
1. Project Overview | Project Name: ManCave Creation for Bugs Bunny | 4. What Didn't Go Well? (Challenges/Issues) | Unforeseen Site Condition / Scope Gap: The need to replace the carpet ($5,000 cost) was the primary issue. This indicates that the initial room assessment did not identify the poor condition of the existing carpet or potential risks associated with it (e.g., damage during installation). While handled by the buffer, it represented an unexpected challenge and cost.
| Project Manager: Porky Pig | 5. Key Lessons Learned | Importance of Detailed Site Assessment: Initial assessments must thoroughly evaluate all existing conditions, including those seemingly outside the direct modification scope (like flooring), to identify potential hidden costs or risks early.
| Project Sponsor: Tom and Jerry |  | Value of Contingency Planning: Allocating a contingency buffer (in this case, $10,000 or ~13% of the budget) is critical for renovation projects to absorb unforeseen issues without derailing the budget.
| Project Owner: Bugs Bunny, Lola Bunny |  | Effective Coordination is Key: Managing multiple vendors and installation timelines requires proactive communication and detailed scheduling to stay on track.
| Planned Dates: May 1, 2025 – September 1, 2025 |  | Clear Scope and Change Management: Adhering to the defined scope and having processes to manage any change requests (though none were mentioned in the scenario) are vital for controlling budget and schedule.
| Actual Completion Date: September 1, 2025 | 6. Recommendations for Future Projects | Enhanced Site Assessment Checklist: Develop and utilize a more detailed checklist for initial site assessments on renovation projects, specifically including evaluation of existing surfaces (floors, walls, ceilings) and basic utilities, regardless of whether they are in scope for modification.
| Project Goal: To design and build a personalized, comfortable Man Cave featuring specified high-end equipment (TVs, sound system, aquarium, bar, security) and memorabilia within a $75,000 budget |  | Maintain Contingency Standards: Continue to include a contingency buffer of 10-15% in budgets for similar renovation projects.
2. Project Performance Summary | Scope: Successfully delivered. All specified features and deliverables (multiple TVs, sound system, seating for eight, 300-gallon saltwater aquarium, carrot juice bar, security system, memorabilia, room finishing) were implemented according to the project charter. |  | Refine Cost Estimation: Use actual costs from this project to refine estimating techniques for future, similar endeavors.
| Schedule: Completed on time. The project met the target completion date of September 1, 2025. |  | Document Vendor Performance: Maintain records of vendor reliability, quality, and pricing for future reference.
Budget: Completed within budget. Final project cost was within the $75,000 target. An unforeseen carpet replacement ($5,000) was successfully covered by the allocated $10,000 contingency buffer.
Quality: High quality achieved. Deliverables met specified requirements, and stakeholder satisfaction (implied by successful completion) is assumed high.
3. What Went Well? (Successes) | Schedule Adherence: Despite the complexity of coordinating multiple vendors and installations (AV, aquarium, security, furniture, bar, painting), the project timeline was met. This indicates effective planning, scheduling, and coordination.
Budget Management: The project successfully stayed within the $75,000 budget limit, even accommodating an unexpected $5,000 cost using the contingency fund appropriately. This suggests strong cost control and potentially successful vendor negotiations.
Scope Delivery: All key deliverables outlined in the charter were successfully implemented, resulting in a fully functional and personalized Man Cave.
Risk Management (Contingency): The contingency buffer was adequately planned and proved essential in handling the unforeseen carpet issue without impacting the overall budget or requiring additional funding requests.
Stakeholder Communication: Implied success – achieving goals suggests communication and expectation management with Bugs, Lola, Tom, and Jerry were effective.
Vendor Coordination: Successful integration of various components (AV, security, aquarium, etc.) points to good vendor selection and management.

## WBS
Work Breakdown Structure (WBS) - ManCave Creation
1. ManCave Creation Project
**1.1 Project Management** (Ongoing throughout project)
1.1.1 Project Initiation & Planning
1.1.1.1 Develop/Review Project Charter
1.1.1.2 Conduct Kick-Off Meeting
1.1.1.3 Gather Detailed Requirements
1.1.1.4 Develop Detailed Schedule
1.1.1.5 Develop Detailed Budget & Allocation
1.1.1.6 Develop Resource Plan
1.1.1.7 Develop Risk Register & Plan Responses
1.1.2 Project Execution Monitoring & Control
1.1.2.1 Track Schedule & Budget Performance
1.1.2.2 Manage Risks & Issues
1.1.2.3 Manage Vendors & Contracts
1.1.2.4 Coordinate Resources
1.1.2.5 Manage Stakeholder Communication & Reporting
1.1.2.6 Manage Scope & Change Control
1.1.3 Project Closure
1.1.3.1 Final Reporting (Budget, Performance)
1.1.3.2 Post-Mortem & Lessons Learned
1.1.3.3 Archive Project Documentation (Knowledge Management)
**1.2 Design**
1.2.1 Room Assessment (Measurements, Condition Check)
1.2.2 Layout Design
1.2.2.1 Develop Layout Options
1.2.2.2 Finalize Layout & Obtain Approval
1.2.3 Finishes Selection (Paint Colors, etc.)
1.2.4 Bar Design Finalization
1.2.5 System Layout Planning
1.2.5.1 AV System Wiring/Placement Plan
1.2.5.2 Security System Layout Plan
**1.3 Procurement**
1.3.1 Vendor Research, Selection & Contracting
1.3.2 Audio/Visual (AV) System Procurement
1.3.2.1 Purchase 77"+ OLED TV
1.3.2.2 Purchase 4x Additional HDTVs
1.3.2.3 Purchase Sound System Components
1.3.3 Furniture Procurement
1.3.3.1 Purchase Stadium/Theater Seating (for 8)
1.3.4 Aquarium System Procurement
1.3.4.1 Purchase 300 Gallon Tank & Stand
1.3.4.2 Purchase Filtration, Lighting, Heater, Supplies
1.3.5 Bar Procurement
1.3.5.1 Purchase Bar Structure/Components
1.3.5.2 Purchase Refrigerator
1.3.6 Security System Procurement
1.3.6.1 Purchase Cameras, DVR, Sensors, Panel
1.3.7 Memorabilia Procurement
1.3.7.1 Select & Purchase Memorabilia Items
1.3.8 Supplies Procurement
1.3.8.1 Purchase Paint & Painting Supplies
1.3.8.2 Purchase Cleaning Supplies
1.3.9 Logistics
1.3.9.1 Schedule Deliveries
1.3.9.2 Coordinate Installation Timing
**1.4 Installation & Setup**
1.4.1 Room Preparation
1.4.1.1 Initial Detailed Cleaning
1.4.1.2 Painting
1.4.1.3 *Carpet Replacement* (Unplanned Work)
1.4.2 Aquarium System Installation
1.4.2.1 Position & Set Up Tank/Stand/Equipment
1.4.2.2 Initiate & Monitor Water Cycling Process
1.4.2.3 Introduce Fish & Coral (Post-Cycling)
1.4.3 AV System Installation
1.4.3.1 Mount/Place TVs
1.4.3.2 Install Speakers & Sound Components
1.4.3.3 Run Wiring & Connect System
1.4.3.4 Configure & Test AV System
1.4.4 Furniture Installation
1.4.4.1 Assemble & Place Seating
1.4.5 Bar Installation
1.4.5.1 Assemble/Install Bar Structure
1.4.5.2 Install Refrigerator
1.4.5.3 Connect Bar Plumbing
1.4.6 Security System Installation
1.4.6.1 Mount Cameras & Sensors
1.4.6.2 Set Up Control Panel & Recording
1.4.6.3 Configure & Test Security System
1.4.7 Final Furnishing & Decoration
1.4.7.1 Arrange & Display Memorabilia
1.4.7.2 Add Decorative Touches
**1.5 Finalization & Handover**
1.5.1 System Integration Testing (All Systems)
1.5.2 Quality Assurance Checks
1.5.3 Final Cleaning
1.5.4 Documentation Handover (Manuals, Warranties)
1.5.5 Owner Training (AV, Aquarium, Security)
1.5.6 Final Project Walkthrough
1.5.7 Obtain Owner Acceptance / Sign-off